## Issue-Log
ISSUE MANAGEMENT LOG
Project Name:			LockedMe.com
Project Manager Name:			Javier Luque
Project Ref:			PR001
ID	Status	Priority	Issue / Description	Owner	Estimated / Resolution / Date	Escalation / Needed / (Y/N)?	Impact	Actions	Date / Identified	Logged By	Actual / Resolution/Completion / Date	Final Resolution / & Follow-on actions
001	Closed	High	BinarySearch not working correctly for Strings	jluque	02/26/22	No	not able to find the first and last filenames of the file array	debug	02/24/22	Jluque	02/26/22	CompareTo needs to be run with ignored case
002	Closed	Medium	Secondary menu is returning to the main menu when executed. It should return to itself.	jluque	02/24/22	no	user can get lost when navigating the operation menu	check the app flow	02/24/22	Jluque	02/24/22	added a while that fixed the flow
003	Closed	high	when user enters a letter when choosing an option. The program is entering into an infinite loop	jluque	02/24/22	no	app shutdowns with an error code	Ask another dev team if they have experience dealing with this type of issue	02/24/22	Jluque	02/26/22	Scanner needed to be re-instantiated at the catch block

## severity-levels
Issue severity	Description
Critical	Issue will stop project progress.
High	Issue will likely impact budget, schedule or scope.
Medium	Issue impact the project, but could be mitigated to avoid an impact on budget, schedule or scope.
Low	Issue is low impact and/or low effort to resolve.