## PRODUCT_BACKLOG
PRODUCT BACKLOG

User Story ID	User Story	Estimate (size)	Priority	Sprint	Task owner	Estimated effort
US001	As an user I need to be able to list The files stored in a folder.	Medium	4	1	Jluque	20
US002	As an user I need to be able to add a file to the existent directory.	Large	5	1	Jluque	20
US003	As an user I need to be able to delete a file in the existent directory.	Medium	4	2	jluque	10
US004	As an user I need to be able to search for a file in the existent directory.	Large	5	2	jluque	22

## PROJECT_DETAILS
PROJECT NUMBER	PR001
PROJECT NAME	LockedMe
PROJECT MANAGER	Javier Luque
DATE	02/15/22
VERSION	0.1

## DROPDOWN_MENUS
PRIORITY		SPRINT
1		1
2		2
3		3
4		4
5		5
		6
		7
		8
		9
		10