## SPRINT_BACKLOG
SPRINT [NUMBER] BACKLOG

ID	User Story	Tasks	Owner	Status	Estimated effort	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7
SP001	As an user I need to be able to list The files stored in a folder.	Code “list files”: Select folder, define a structure, sort and display	Jluque	Completed	20	8
		Create empty menus	Jluque	Completed			8
		Demo, show list files functionalities	Jluque	Completed				2	2
	As an user I need to be able to add a file to the existent directory.	Code Insert file: define folder, check duplicated exception, store	Jluque	Completed	20			6	3
		Prepare and execute demo	Jluque	Completed					3	8
SP002	As an user I need to be able to delete a file in the existent directory.	Code Delete file: define folder, watch checked exceptions.	Jluque	Completed	10	8
		other exceptions	jluque	Completed			2
	As an user I need to be able to search for a file in the existent directory.	Code Search: define folder, check letter case	jluque	Completed	22		6	2
		Prepare a complete demo	jluque	Completed				4	4
		Complete any changes required from Demo	jluque	Completed					4	2
					72	16	16	14	16	10	0	0

## PROJECT_DETAILS
PROJECT NUMBER	PR001
PROJECT NAME	LockedMe
PROJECT MANAGER	Javier Luque
DATE	02/15/22
VERSION	0.1